## Overview
ORACLE — Strategy Development Tracker
See the level before price arrives · NQ / MNQ Futures · TradingView Pine Script v5 · All Versions
VERSION SUMMARY
# | Version | Status | Release | Trades | Win Rate | PF | Focus
v1.0 | Oracle — Original | COMPLETE | Mar 2026 | N/A | N/A | N/A | Key levels, 6 signals, fixed/trailing SL, basic dashboard, daily P&L limits
v1.1 | Oracle — Risk Additions | COMPLETE | Mar 2026 | N/A | N/A | N/A | ATR SL, Breakeven, Partial close, Re-entry block, Win streak lock-in, consecutive loss alert
v1.2 | Oracle — Signal Improvements | COMPLETE | Mar 2026 | N/A | N/A | N/A | EMA filter, Volume filter, Friday Close directional bias, Signal spacing, Session P&L stops
v1.3 | Oracle — P&L Tracking | COMPLETE | Mar 2026 | N/A | N/A | N/A | Monthly/Annual tracker, Contract calculator, Reload-safe weekly/monthly/annual scan functions
v1.4 | Oracle — Execution | COMPLETE | Mar 2026 | N/A | N/A | N/A | Execution alerts (PineConnector), News blackout, R:R ratio row, Streak tracking
v1.5 | Oracle — Final (LIVE) | LIVE | Mar 2026 | 136 (BT) | 66.9% (BT) | 1.731 (BT) | Tick-level SL execution, isToday timezone fix, Session P&L attribution fix, consecutive loss streak fix
v1.6 | Oracle — Level Bias | PENDING | Post 19 Apr 2026 | TBD | TBD | TBD | Level rejection/retest/flip, Dynamic R:R, 18-item update, bug fixes, removals, additions
v1.6S | Oracle — Sentiment | PENDING | After v1.6 | TBD | TBD | TBD | HTF sentiment indicator — 5m/15m/30m/1H/2H/3H/4H/Daily selectable
v1.7 | Oracle — Three Session Merge | PENDING | Q3 2026 | TBD | TBD | TBD | Asian/London ranges, FVG, Session bias, Multi-timeframe — merge with NQ Three Session Strategy v3
FORWARD TEST SUMMARY — v1.5 (22 Mar 2026 → 19 Apr 2026)
Week | Dates | SL | TP | Target | Result | Notes | Issues
W1 | 22–28 Mar | 50pts | 20pts | $1,000 | +$1,057.50 ✓ | Weekly target hit. Loss limit fired 26 Mar. | EMA not blocking counter-trend longs. All exits via duration timer at ±3-4pts.
W2 | 30 Mar–5 Apr | 40pts→30pts | 20pts | $1,000 | In progress | SL reducing to 30pts. Level flip confirmed 1 Apr. | Asian high triple rejection observed. Level bias validated.
W3 | 6–12 Apr | 30pts | 20pts | $1,000 | Pending
W4 | 13–19 Apr | 30pts | 20pts | $1,000 | Pending | Final week before v1.6 build

## v1.0-v1.4
ORACLE v1.0 — v1.4 — Development Versions — Foundation Build
Status: COMPLETE · Release: March 2026 · Scripts: Oracle_Basic/Pro/Master_v1.0 through v1.4
CHANGELOG — What Was Built / Changed / Removed
# | Feature / Change | Category | Priority | Detail | Files
1.0-1 | Key level drawing | Added | Core | PDH, PDL, PWH, PWL, PMH, PML, Prev Friday Close drawn automatically from request.security(). All extend right across chart. | Master
1.0-2 | Six signal types | Added | Core | Pin Bar Rejection, Engulfing (Strict/Relaxed), 3-Candle Reversal, Liquidity Sweep+Return, Morning/Evening Star, Momentum Candle. | Master
1.0-3 | Fixed and trailing SL | Added | Core | Toggle between fixed stop loss (pts) and ATR-based trailing stop. Both work with tick-level or bar-close execution. | Master
1.0-4 | Basic dashboard table | Added | Core | Session table showing London/NY trades and P&L. Weekly row. BOT STATUS header row. | Master
1.0-5 | Daily P&L limits | Added | Core | Daily profit target and daily loss limit — both stop Oracle for the rest of the day when hit. | Master
1.1-1 | ATR dynamic SL | Added | HIGH | ATR period and multiplier configurable. Dynamic SL width scales with recent volatility. | Master
1.1-2 | Breakeven move | Added | MEDIUM | Optional move-to-breakeven when price moves N points in trade's favour. | Master
1.1-3 | Partial close (TP1/TP2) | Added | MEDIUM | Close partial position at TP1, remainder runs to TP2. Scheduled for removal in v1.6. | Master
1.1-4 | Re-entry block | Added | MEDIUM | After a win, block re-entry at same level for N bars to prevent over-trading. | Master
1.1-5 | Win streak lock-in | Added | LOW | After N consecutive wins, tighten SL to protect gains. | Master
1.1-6 | Consecutive loss alert | Added | HIGH | Alert fires after N consecutive losses. Threshold configurable. Default: 2. | Master
1.2-1 | EMA trend filter | Added | HIGH | EMA period configurable. Longs only when price above EMA. Shorts only when below. Prevents counter-trend entries. | Master
1.2-2 | Volume filter | Added | HIGH | Entry candle volume must exceed N% of 20-bar average. Default 100%. Low-volume signals filtered out. | Master
1.2-3 | Friday Close directional bias | Added | HIGH | touchingLongLevel() / touchingShortLevel() — Friday Close only qualifies as support for longs from below and resistance for shorts from above. | Master
1.2-4 | Signal spacing | Added | MEDIUM | Minimum N bars between entries. Prevents signal clusters at same level. Default: 3 bars. | Master
1.2-5 | London/NY session loss limits | Added | LOW | Optional per-session loss limits. Both disabled in live testing. Scheduled for removal in v1.6. | Master
1.3-1 | Monthly P&L tracker | Added | MEDIUM | Monthly P&L derived by scanning strategy.closedtrades.exit_time() — reload-safe. | Master
1.3-2 | Annual target tracker | Added | MEDIUM | Year-to-date P&L vs configurable annual target. Shows % achieved and pro-rata pace. | Master
1.3-3 | Contract calculator | Added | LOW | Based on annual target, win rate projection and TP pts — estimates required contracts. Displayed in dashboard. | Master
1.3-4 | Reload-safe scan functions | Added | HIGH | calcWeeklyStats(), calcMonthlyPnL(), calcAnnualPnL(), calcWeekWinLoss() — all scan closed trades on every bar, surviving chart reloads. | Master
1.4-1 | Execution alerts (PineConnector) | Added | HIGH | alert() calls with Entry, SL, TP values. Compatible with PineConnector webhook for automated execution. | Master
1.4-2 | News blackout window | Added | MEDIUM | Configurable time range to block trading around scheduled news events. | Master
1.4-3 | R:R ratio in dashboard | Added | LOW | Displays current TP/SL ratio in the dashboard summary table. | Master
1.4-4 | Streak tracking | Added | MEDIUM | Consecutive win and loss streak tracked and displayed. Feeds into win streak lock-in and consecutive loss alert. | Master
BACKTEST RESULTS
Run | Period | Trades | Win Rate | P&L | Profit Factor
N/A | No formal backtest run for v1.0-v1.4 | N/A | N/A | N/A | N/A
DEVELOPMENT NOTES AND OBSERVATIONS
• v1.0-v1.4 were development iterations — no formal backtest was run until v1.5 optimisation. • All features added in v1.0-v1.4 were carried forward into v1.5. • Partial Close and Session Loss Limits (added v1.1 and v1.2) are scheduled for removal in v1.6 based on live testing showing they are not needed. • The EMA filter added in v1.2 has a known bug — it does not check slope direction, only price vs EMA position. Fix scheduled for v1.6.

## v1.5 (LIVE)
ORACLE v1.5 — Final Production Version — Currently Live
Status: LIVE · Release: 22 March 2026 · Scripts: Oracle_Basic_v1.5 · Oracle_Pro_v1.5 · Oracle_Master_v1.5
CHANGELOG — What Was Built / Changed / Removed
# | Feature / Change | Category | Priority | Detail | Files
1 | Tick-level SL execution | Fixed | CRITICAL | Added close_entries_rule='ANY' and calc_on_every_tick=true to strategy declaration. SL now closes intra-bar at the stop price rather than waiting for bar close. Eliminates SL overshoot. | All
2 | isToday timezone fix | Fixed | CRITICAL | todayYear/Month/Day now use sessionTZ consistently. Previously used syminfo.timezone (CME Chicago time) causing London session trades (03:00-08:00) to appear as yesterday — blocking all signals. | All
3 | Session P&L attribution | Fixed | HIGH | London and NY P&L now tracked incrementally on each bar using exit_time comparison. Old approach showed identical figures for both sessions. | All
4 | Weekly P&L reload survival | Fixed | HIGH | Weekly/monthly/annual P&L derived by scanning strategy.closedtrades.exit_time() on every bar. Old baseline snapshot was lost on chart reload. | All
5 | Session open detection fix | Fixed | HIGH | londonJustOpened and nyJustOpened changed from == to >= comparison. Exact minute match missed sessions when no bar landed at exactly 03:00 on 1-min chart. | All
6 | Friday Close direction fix | Fixed | MEDIUM | touchingLongLevel() and touchingShortLevel() added. Friday Close now qualifies as support for longs (price from below) and resistance for shorts (from above) only. | All
7 | Annual reset syntax fix | Fixed | LOW | time('Y') is invalid Pine Script. Changed to time('12M') for annual period reset. | All
8 | Trailing SL continuation fix | Fixed | LOW | Trailing + at end of long lines caused 'end of line without continuation' errors. Split into intermediate variables. | All
9 | Consecutive loss streak fix | Fixed | MEDIUM | Streak counter was resetting incorrectly on draw exits. Now correctly tracks consecutive losses across all exit types. | All
10 | Three-tier version structure | Added | HIGH | Oracle Basic (advanced settings hidden/locked, 20-min duration hardcoded), Oracle Pro (all settings visible), Oracle Master (development version, source for Basic and Pro). | All
SETTINGS — Configuration at This Version
Group | Setting | Value | Applies To | Notes | Change from Prior
Signals | All 6 signals | ON | All | All signal types enabled
Signals | Engulfing type | Strict | All | Full range engulfing only
Signals | Momentum multiplier | 1.5x | All | Min body size threshold
Filters | Volume filter | ON at 100% | All | 100% of 20-bar average
Filters | EMA filter | ON at 50 | All | Price vs EMA position check only — slope check pending v1.6
Filters | Signal spacing | ON at 3 bars | All | Minimum 3 bars between entries
Risk | Stop Loss | 30 points | All | $180 at 3 MNQ. Reverted from 50pts (W1) and 40pts (W2) during live test.
Risk | Take Profit | 20 points | All | $120 at 3 MNQ
Risk | Touch zone | 8 points | All | Level proximity threshold
Risk | SL type | Fixed | All | ATR disabled — caused Run 1 problems
Risk | Duration | 20 minutes | All | Hardcoded in Basic, configurable in Pro
Contracts | Starting contracts | 3 MNQ | Live | $6/point
P&L | Daily profit target | $300 | Live | Stop trading when hit
P&L | Daily loss limit | $700 | Live | Hard stop for the day
P&L | Weekly target | $1,000 | Live | Conservative starting point | Week 1: hit at $1,057.50
Days | Monday | ON | Live
Days | Tuesday | OFF | Live | Worst performing day across all backtests
Days | Wednesday | ON | Live |  | Re-enabled in Run 4 — contributed +$747
Days | Thursday | ON | Live | Best day — 72.7% WR Run 4
Days | Friday | ON | Live
Sessions | London | 03:00-08:00 | All
Sessions | New York | 08:00-16:00 | All |  | Extended to 16:00 in Run 4
Sessions | Flat time | 17:00-17:59 | All | Close all positions before NY close
Blackouts | Blackout 1 | 06:00-09:00 | All | Pre-market London
Blackouts | Blackout 2 | 10:00-15:00 | All | NY afternoon | Review: may start at 11:00 in v1.6
Mode | Backtest Mode | OFF for live | All | MUST be OFF — check daily
BACKTEST RESULTS
Run | Period | Trades | Win Rate | P&L | Profit Factor
Run 1 | 21 Mar 25 – 21 Mar 26 | 68 | 52.9% | +$2,507.50 | 1.217
Run 2 | 21 Mar 25 – 21 Mar 26 | 293 | 67.9% | +$217.50 | 1.016
Run 3 | 21 Mar 25 – 21 Mar 26 | 142 | 64.8% | +$2,752.50 | 1.329
Run 4 ★ | 21 Mar 25 – 21 Mar 26 | 136 | 66.9% | +$4,825.50 | 1.731
LIVE FORWARD TEST LOG
Week | Dates | SL/TP | Result | Key Events | Issues Observed
Week 1 | 22–28 Mar 2026 | SL 50pts / TP 20pts | +$1,057.50 ✓ Target hit | Weekly target $1,000 hit. Daily loss limit fired 26 Mar. NQ down 282pts on 26 Mar. | EMA not blocking counter-trend longs. All exits at ±3-4pts via duration timer. SL at 50pts producing 0.4:1 R:R.
Week 2 | 30 Mar–5 Apr 2026 | SL 40pts→30pts / TP 20pts | In progress | SL reducing to 30pts. Asian high triple rejection 1 Apr confirmed level bias pattern. NQ up 757pts 31 Mar, up 367pts 1 Apr. | Asian high acting as resistance documented. Level flip observed 1 Apr. Three Session strategy running in parallel.
Week 3 | 6–12 Apr 2026 | SL 30pts / TP 20pts | Pending
Week 4 | 13–19 Apr 2026 | SL 30pts / TP 20pts | Pending | Final week. CSV export and full review on 19 Apr 2026.
DEVELOPMENT NOTES AND OBSERVATIONS
• v1.5 is the first version with a formal 12-month backtest (4 runs). Run 4 is the optimised configuration. • Three version tiers introduced: Basic (settings locked), Pro (fully configurable), Master (development source). • The R:R of 0.67:1 (TP 20 / SL 30) requires a consistent 60%+ win rate to be profitable. • The Three Session Strategy v3 is running in parallel with v1.5 during the forward test for comparative data. • No code changes until 4-week CSV data is delivered on 19 April 2026. • Reference cases documented: PDH overnight flip (28 Mar), Asian high double rejection (1 Apr AM), Full three-phase pattern (1 Apr full day), Prev Friday Close rejection (31 Mar).

## v1.6 Standard
ORACLE v1.6 Standard — Level Bias System — Post-Testing Update
Status: PENDING · Release: Post 19 April 2026 · Scripts: Oracle_Basic_v1.6 · Oracle_Pro_v1.6 · Oracle_Master_v1.6
CHANGELOG — What Was Built / Changed / Removed
# | Feature / Change | Category | Priority | Detail | Files
1 | Level Rejection and Retest model | Core | CRITICAL | Level bias per level type — PDH/PWH/PMH shorts only, PDL/PWL/PML longs only, Prev Friday Close by approach side. Two-touch entry (Touch 1 flags, Touch 2 fires). Flip detection when price closes decisively through level. Applies to all 8 level types. | All
1a | Dynamic R:R | Core | HIGH | SL placed 5pts beyond rejection candle high/low. TP = 2x SL distance automatically. Removes fixed 20pt TP / 30pt SL. Improves R:R from 0.67:1 to 2:1. Aligns with Three Session strategy approach. | All
2 | EMA filter slope check | Fixed | HIGH | Add slope direction check to emaBullOk condition. Currently only checks price vs EMA position — needs to also verify EMA is trending in the correct direction. | All
3 | Session hours gate fix | Fixed | HIGH | Signals firing at 19:00-20:30 UTC-4 — outside both London and NY session windows. isTradingSession gate investigation and fix. | All
4 | Level touch alert fix | Fixed | MEDIUM | Alerts triggering on wick touches without valid signal body pattern. Add bar close proximity check to level touch detection. | All
5 | Tuesday disabled fix | Fixed | MEDIUM | Signals observed on 5-minute chart on Tuesday 24 March despite Tuesday being disabled. Confirm and fix. | All
6 | Duration vs TP review | Changed | MEDIUM | Review whether 20-minute duration is appropriate with dynamic R:R. If TP is now 2x the SL distance, price may need more time. Possibly increase or remove duration limit. | All
7 | Signal spacing increase | Changed | MEDIUM | Increase minimum bars between signals from 3 to 5+ bars to reduce clustering observed in live testing. | All
8 | Blackout 2 start time review | Changed | LOW | Consider changing Blackout 2 start from 10:00 to 11:00 based on 31 Mar Prev Friday Close rejection at 10:30 being a high-quality missed setup. | All
9 | Remove Partial Close | Removed | LOW | Not required with tight TP and dynamic R:R. Removes usePartialClose, tp1Points, tp2Points, partialClosed variable and split exit logic. | All
10 | Remove London Session Loss Limit | Removed | LOW | Not required. Removes useLondonSessionStop, londonSessionLoss, londonSessionStopped. | All
11 | Remove NY Session Loss Limit | Removed | LOW | Not required. Removes useNYSessionStop, nySessionLoss, nySessionStopped. | All
12 | Monthly P&L in dashboard | Added | MEDIUM | Add monthly breakdown table and bar chart to Performance Dashboard HTML. Data already calculated in script — needs surfacing. | Dashboard
13 | Live trade management lines | Added | MEDIUM | Entry line (blue), SL line (red), TP line (green dashed), trailing trigger (orange), floating live P&L label. Draw on entry, delete on exit via line.new() and line.delete(). | All
SETTINGS — Configuration at This Version
Group | Setting | Value | Applies To | Notes | Change from Prior
Risk | Stop Loss | At structure (dynamic) | All | 5pts beyond rejection candle high/low | Changed from 30pts fixed
Risk | Take Profit | 2x SL distance (dynamic) | All | Scales automatically with SL | Changed from 20pts fixed
Risk | Target R:R | 2:1 | All | Requires only 34%+ WR to break even | Improved from 0.67:1
Filters | Signal spacing | 5+ bars | All | Increased from 3 bars | Changed from 3 bars
Blackouts | Blackout 2 | 11:00-15:00 | All | TBD — pending live data review | Possibly changed from 10:00
BACKTEST RESULTS
Run | Period | Trades | Win Rate | P&L | Profit Factor
TBD | To be run after implementing v1.6 changes | TBD | TBD | TBD | TBD
LIVE FORWARD TEST LOG
Week | Dates | SL/TP | Result | Key Events | Issues Observed
W1-W4 | Post 19 Apr 2026 | Dynamic R:R (2:1) | Pending | Minimum 4 weeks live before v1.6 Sentiment begins
DEVELOPMENT NOTES AND OBSERVATIONS
• v1.6 is the most significant architectural change since the original build. • The Level Rejection and Retest model with Flip Detection is the foundation of v1.6. • Dynamic R:R changes the fundamental profit/loss profile — the backtest must be rerun against v1.6 before going live. • All 13 changelog items must be implemented before the version is released. • The User Guide will be updated to v4 when v1.6 is released. • No version 1.6 code changes begin until the 4-week v1.5 CSV is delivered on 19 April 2026.

## v1.6 Sentiment
ORACLE v1.6 Sentiment — HTF Sentiment Layer — Separate Test Period
Status: PENDING · Release: After v1.6 Standard baseline (est. Jun 2026) · Scripts: Oracle_Basic_v1.6_Sentiment · Oracle_Pro_v1.6_Sentiment · Oracle_Master_v1.6_Sentiment
CHANGELOG — What Was Built / Changed / Removed
# | Feature / Change | Category | Priority | Detail | Files
14 | HTF sentiment indicator | Added | HIGH | Selectable timeframe input: 5m/15m/30m/1H/2H/3H/4H/Daily. Sentiment score built from 5 factors on selected HTF: EMA position, EMA slope, nearest level type, recent signal bias, session context. Updates only on HTF bar close. Displayed in summary table with colour coding. | Sentiment only
15 | Historical sentiment in dashboard | Added | MEDIUM | Historical sentiment panel in Performance Dashboard HTML based on loaded trade direction bias and win rate by direction from CSV data. | Dashboard
16 | HTF sentiment as entry gate (evaluate) | Added | LOW | Longs only when HTF sentiment Neutral or Bullish. Shorts only when Neutral or Bearish. Evaluate after 4 weeks of Sentiment version data — do not implement until evidence supports it. | Sentiment only
SETTINGS — Configuration at This Version
Group | Setting | Value | Applies To | Notes | Change from Prior
Sentiment | Sentiment timeframe | 5m/15m/30m/1H/2H/3H/4H/Daily | Sentiment only | Selectable dropdown — updates on HTF bar close | New setting
Sentiment | Sentiment display | ON | Sentiment only | Shows in summary dashboard table | New setting
Sentiment | Sentiment as gate | OFF initially | Sentiment only | Enable only after 4 weeks of data confirms value | New setting
BACKTEST RESULTS
Run | Period | Trades | Win Rate | P&L | Profit Factor
N/A | Sentiment version — no separate backtest required initially | N/A | N/A | N/A | N/A
LIVE FORWARD TEST LOG
Week | Dates | SL/TP | Result | Key Events | Issues Observed
W1-W4 | After v1.6 Standard baseline | Same as v1.6 Standard + sentiment | Pending | Compare sentiment-gated vs unfiltered results
DEVELOPMENT NOTES AND OBSERVATIONS
• v1.6 Sentiment is kept as a separate set of scripts to maintain a clean comparison baseline against v1.6 Standard. • The sentiment calculation uses request.security() to fetch HTF data — updates only on HTF bar close. • The 2H and 3H timeframe options were specifically requested (valid Pine Script strings: '120' and '180'). • Prerequisite: v1.6 Standard must be live and stable for a minimum of 4 weeks before Sentiment version testing begins. • If sentiment gating is eventually enabled (Item 16), it would directly address the EMA filter issue by using a higher-quality trend confirmation.

## v1.7
ORACLE v1.7 — Three Session Merge — Asian, London, FVG, Multi-Timeframe
Status: PENDING · Release: Q3 2026 (est. Sep–Oct 2026) · Scripts: Oracle_Basic_v1.7 · Oracle_Pro_v1.7 · Oracle_Master_v1.7
CHANGELOG — What Was Built / Changed / Removed
# | Feature / Change | Category | Priority | Detail | Files
19 | Multi-timeframe selector | Added | HIGH | Auto/1-min/5-min dropdown. Auto detects chart timeframe via timeframe.period. Scaled parameters per timeframe: max duration (20 bars on 1-min = 4 bars on 5-min, increase to 12 bars / 60 mins), signal spacing (3 bars = 3 mins on 1-min vs 15 mins on 5-min), touch zone (8pts on 1-min, 10-12pts on 5-min). Session times and blackouts use clock times — no change needed. | All
20 | Asian session range | Added | CRITICAL | Track and draw Asian H/L/Midpoint (18:00-06:00 NY time). Asian high default = resistance (shorts only). Asian low default = support (longs only). Same flip detection as all other levels. Confirmed by live observation 1 Apr 2026 — triple rejection at Asian high, 80pt move. | All
21 | London session range | Added | HIGH | Track and draw London H/L/Midpoint (03:00-11:00 NY time). Same level bias and flip detection as Asian. London midpoint used for NY session bias filter. | All
22 | Asian sweep signals | Added | CRITICAL | Bull sweep: price dips below Asian low + sweepPts buffer then closes above (long). Bear sweep: spikes above Asian high + sweepPts buffer then closes below (short). Body ratio filter (min 0.4). Min 10 bars between sweeps. Signal label shows Entry/SL/TP. Confirmed: 1 Apr 2026 Asian low sweep at 08:45 → 140pt recovery. | All
23 | Fair Value Gap signals | Added | HIGH | Bull FVG: candle 3 low > candle 1 high by minGap (2pts default). Bear FVG: candle 3 high < candle 1 low. Zone drawn as coloured box on chart extending right. Signal fires when price re-enters the zone. Up to 5 active zones per direction simultaneously (Latest Only option available). Zones cleared on session transition. | All
24 | Cascading session bias filter | Added | HIGH | London FVG and signal entries filtered by Asian session bias (price above/below Asian midpoint). NY entries filtered by London bias (falls back to Asian if London midpoint not set). Adds intelligence layer on top of existing EMA filter. Prevents counter-trend FVG entries in choppy sessions. | All
25 | Sweep conflict guard | Added | MEDIUM | When Asian sweep long fires, block bear FVG signals for N bars (configurable, default 10). When Asian sweep short fires, block bull FVG signals. Prevents strategy taking contradictory FVG signal immediately after a sweep in the opposite direction. | All
26 | Psychological level dots | Added | LOW | Round number levels every 100pts shown as small dots on chart. Optional toggle. NQ tends to react at round numbers — useful visual reference. | All
27 | Session background shading | Added | LOW | Light background colour per session: Asian (blue), London (orange), NY (yellow). Optional toggle. Helps quickly identify which session is active on the chart. | All
SETTINGS — Configuration at This Version
Group | Setting | Value | Applies To | Notes | Change from Prior
Timeframe | Chart timeframe mode | Auto / 1-min / 5-min | All | Auto detects and scales parameters | New setting
Sessions | Asian session | 18:00-06:00 NY | All | Tracked for H/L/Mid and sweep signals | New setting
Sessions | London session | 03:00-11:00 NY | All | Tracked for H/L/Mid and bias filter | New setting
Sweeps | Sweep buffer | 3 points | All | Price must exceed Asian H/L by this amount | New setting
Sweeps | Min body ratio | 0.4 | All | Rejection candle body must be 40%+ of range | New setting
FVG | Min FVG size | 2 points | All | Gap must be at least 2pts to qualify | New setting
FVG | Latest FVG only | OFF | All | OFF = up to 5 zones active. ON = latest only. | New setting
Bias | Session bias filter | ON | All | Cascading Asian→London→NY bias gates | New setting
Guard | Sweep conflict guard | 10 bars | All | Blocks opposite FVG for 10 bars after sweep | New setting
Visual | Psych level dots | ON | All | Round number dots every 100pts | New setting
Visual | Session backgrounds | ON | All | Asian/London/NY background shading | New setting
BACKTEST RESULTS
Run | Period | Trades | Win Rate | P&L | Profit Factor
1-min BT | To be run after v1.7 is built | TBD | TBD | TBD | TBD
5-min BT | Prerequisite — must complete before v1.7 release | TBD | TBD | TBD | TBD
LIVE FORWARD TEST LOG
Week | Dates | SL/TP | Result | Key Events | Issues Observed
1-min FT | After v1.7 build | Dynamic R:R (2:1) + Three Session | Pending | Minimum 4 weeks
5-min FT | Prerequisite — parallel test | Scaled params | Pending | Minimum 4 weeks concurrent with v1.6
DEVELOPMENT NOTES AND OBSERVATIONS
• v1.7 merges Oracle v1.6 with NQ Three Session Strategy v3 (Pine Script v6 — will require upgrade to v6 or adaptation to v5). • This is the largest build to date — 9 new features plus multi-timeframe scaling. • PREREQUISITES (all 4 must be met): 1. v1.6 Standard live 4+ weeks. 2. 5-min backtest with scaled parameters complete. 3. 5-min forward test 4+ weeks. 4. Parameters confirmed for both timeframes. • Earliest possible v1.7 release: late July 2026. Realistic estimate: September-October 2026. • The NQ Three Session Strategy v3 is written in Pine Script v6. Oracle is v5. Merge will require either upgrading Oracle to v6 or porting the Three Session logic to v5. • Reference cases for v1.7 build: Case 1 (28 Mar — PDH overnight flip), Case 2 (1 Apr AM — Asian high double rejection), Case 3 (1 Apr full — three-phase sweep/rejection/flip), Case 4 (31 Mar — Prev Friday Close rejection). • The Three Session strategy uses a 2:1 R:R ratio — consistent with the dynamic R:R approach introduced in v1.6. • Running Oracle v1.5 and Three Session v3 in parallel during the forward test provides comparative data for v1.7 parameter decisions.

## Backtest Results
ORACLE — Backtest Results (All Runs)
Period: 21 Mar 2025 — 21 Mar 2026 · Symbol: MNQM2026 · Timeframe: 1-minute · 3 MNQ contracts
RUN COMPARISON
Run | Configuration | Trades | Win Rate | P&L | PF | Avg Win | Max DD
Run 1 | ATR SL (period 5, 1x) · Vol 180% | 68 | 52.9% | $2,507.50 | 1.217 | $391 | $3,315
Run 2 | Fixed SL · Blackout 06-09 · Vol 100% | 293 | 67.9% | $217.50 | 1.016 | $71 | $2,334
Run 3 | EMA filter · TP 20pts · Blackout 10-15 | 142 | 64.8% | $2,752.50 | 1.329 | $120.90 | $1,275
Run 4 ★ | SL 30pts · TP 20pts · tick exec · all fixes | 136 | 66.9% | $4,825.50 | 1.731 | $125.50 | $831
RUN 4 DETAILED METRICS
Metric | Value | Metric | Value | Metric | Value | Metric | Value
Total P&L | +$4,825.50 | Win Trades | 91 | Loss Trades | 45 | Win Rate | 66.9%
Profit Factor | 1.731 | Avg Win | +$125.50 | Avg Loss | -$146.60 | Max DD | $831
Long P&L | +$3,198 | Long WR | 65.3% | Short P&L | +$1,627.50 | Short WR | 64.2%
Best Day | Thursday | Best Day WR | 72.7% | Best Hour | 03:00-05:00 | Max Win Streak | 8
P&L BY DAY
Day | Trades | Win Rate | P&L
Monday | 24 | 62.5% | +$571.50
Tuesday (OFF) | 0 | — | —
Wednesday | 26 | 61.5% | +$747.00
Thursday | 33 | 72.7% | +$1,920.00
Friday | 53 | 67.9% | +$1,587.00

## v1.6 Update Plan
ORACLE v1.6 — Post-Testing Update Plan (18 Items)
Triggered: 4-week CSV delivered 19 Apr 2026 · No implementation until forward test complete
Priority 1 — Core Architecture
# | Priority | Item | Detail | Scope | Status
1 | CRITICAL | Level Rejection and Retest model with Flip Detection | Level bias per type, two-touch entry, flip detection, dynamic R:R (SL at structure, TP = 2x). All 8 level types. | All | OPEN
1a | HIGH | Dynamic R:R — SL at structure, TP = 2x distance | Removes fixed 20pt/30pt. Improves R:R from 0.67:1 to 2:1. | All | OPEN
Priority 2 — Bug Fixes
# | Priority | Item | Detail | Scope | Status
2 | HIGH | EMA filter slope direction check | Needs slope check in addition to price vs EMA position. | All | OPEN
3 | HIGH | Signals firing outside session hours (19:00-20:30) | isTradingSession gate fix required. | All | OPEN
4 | MEDIUM | Incorrect alerts at level touches | Bar close proximity check on level touch detection. | All | OPEN
5 | MEDIUM | Tuesday signals appearing when disabled | Confirm on 1-minute data and fix. | All | OPEN
Priority 3 — Settings Reviews
# | Priority | Item | Detail | Scope | Status
6 | MEDIUM | Duration timer vs TP relationship | Review with dynamic R:R — may need increase or removal. | All | OPEN
7 | MEDIUM | Signal spacing increase | 3 bars to 5+ bars — reduce live clustering. | All | OPEN
8 | LOW | Blackout 2 start time (10:00 vs 11:00) | 31 Mar case — high quality setup at 10:30 blocked. | All | OPEN
Priority 4 — Removals
# | Priority | Item | Detail | Scope | Status
9 | LOW | Remove Partial Close (TP1/TP2) | Not required with dynamic R:R. | All | OPEN
10 | LOW | Remove London Session Loss Limit | Not required with tight TP. | All | OPEN
11 | LOW | Remove NY Session Loss Limit | Not required with tight TP. | All | OPEN
Priority 5 — Additions
# | Priority | Item | Detail | Scope | Status
12 | MEDIUM | Monthly P&L in Performance Dashboard | Breakdown table and bar chart. Data already in script. | Dashboard | OPEN
13 | MEDIUM | Live trade management lines | Entry/SL/TP/trail lines + live P&L label. Draw on entry, delete on exit. | All | OPEN

## Roadmap
ORACLE — Development Roadmap
No version begins until all prerequisites for that version are confirmed and documented
VERSION ROADMAP
Version | Status | Timeline | Min Duration | Focus | Prerequisites | Scripts
v1.5 | LIVE | 22 Mar 2026 | 4 weeks (→19 Apr) | Tick-level SL, timezone fix, session P&L attribution, all bug fixes from development | None — current production | Basic/Pro/Master v1.5
v1.6 Standard | PENDING | Post 19 Apr 2026 | 4 weeks min | Level Rejection/Retest/Flip, Dynamic R:R, 18-item update | 4-week v1.5 CSV delivered | Basic/Pro/Master v1.6
v1.6 Sentiment | PENDING | After v1.6 baseline | 4 weeks min | HTF sentiment indicator — 5m/15m/30m/1H/2H/3H/4H/Daily | v1.6 Standard live and stable 4+ weeks | Basic/Pro/Master v1.6 Sentiment
v1.7 | PENDING | Q3 2026 (est.) | 4 weeks min | Asian/London ranges, FVG, Session bias, Multi-timeframe — full Three Session merge | 1. v1.6 live 4wks 2. 5-min BT done 3. 5-min FT 4wks 4. Params confirmed | Basic/Pro/Master v1.7

## Optimum Settings
ORACLE v1.5 — Optimum Settings (Run 4 Configuration)
Do not change these settings during the 4-week forward test. All changes driven by data after 19 Apr 2026.
SIGNAL TYPES
Setting | Value | Applies To | Notes | Warning / Change History
All 6 signals | ON | All
Engulfing type | Strict | All | Full range must be engulfed
Momentum multiplier | 1.5x | All | Min body size
Volume filter | ON at 100% | All | 100% of 20-bar avg
EMA filter | ON at Period 50 | All | Price vs EMA only — slope fix in v1.6 | Known bug: slope not checked
Signal spacing | ON at 3 bars | All | Min bars between entries
RISK MANAGEMENT
Setting | Value | Applies To | Notes | Warning / Change History
Stop Loss | 30 points | All | $180 at 3 MNQ | REDUCED: was 50pts (W1), 40pts (W2)
Take Profit | 20 points | All | $120 at 3 MNQ — R:R 0.67:1 | Dynamic R:R planned for v1.6
Touch zone | 8 points | All | Level proximity threshold
SL type | Fixed | All | Do NOT switch to ATR | ATR caused Run 1 problems
Duration | 20 minutes | All | Hardcoded in Basic | Review for v1.6 with dynamic R:R
Contracts | 3 MNQ | Live | $6/point | Scale only after 4+ weeks live
DAILY P&L LIMITS
Setting | Value | Applies To | Notes | Warning / Change History
Daily profit target | $300 | Live | Bot stops for the day
Daily loss limit | $700 | Live | Hard stop
Weekly target | $1,000 | Live | Conservative starting point | Hit Week 1: +$1,057.50
Consecutive loss alert | ON at 2 | All | Alert after 2 consecutive losses
London session loss limit | OFF | All | Removal planned v1.6
NY session loss limit | OFF | All | Removal planned v1.6
TRADING DAYS
Setting | Value | Applies To | Notes | Warning / Change History
Monday | ON | Live
Tuesday | OFF | Live | Consistently worst day — all 4 backtests
Wednesday | ON | Live | Re-enabled Run 4 — +$747
Thursday | ON | Live | Best day — 72.7% WR, +$1,920
Friday | ON | Live | 67.9% WR, +$1,587
SESSIONS AND BLACKOUTS
Setting | Value | Applies To | Notes | Warning / Change History
Timezone | America/New York | All | Or Exchange — match broker
London | 03:00-08:00 | All
NY | 08:00-16:00 | All | Extended to 16:00 in Run 4
Flat time | 17:00-17:59 | All | Close all positions
Blackout 1 | 06:00-09:00 | All | Pre-market London
Blackout 2 | 10:00-15:00 | All | NY afternoon | Review: start at 11:00 in v1.6?
Backtest Mode | OFF — check daily | ALL | MOST CRITICAL SETTING | Check before EVERY session

## Forward Test Log
ORACLE v1.5 — Forward Test Log (22 Mar – 19 Apr 2026)
Live trading on MNQM2026 · 1-minute chart · 3 MNQ contracts · Backtest Mode OFF
DAILY SESSION LOG
Date | Day | Trades | P&L | Bot Status | Key Observation | Issues Logged
22 Mar | Sun | 0 | $0 | Day off | Week 1 begins. Chart confirmed on 1-min. Backtest Mode OFF.
23 Mar | Mon | 5 | -$126 | Daily loss limit hit 11:01 | Counter-trend longs in downtrend. All exits at ±4pts. NQ -282pts. | EMA filter not blocking longs. Duration timer dominating.
24 Mar | Tue | 0 | $0 | Day off | Tuesday correctly disabled. | Signals visible on 5-min — confirm on 1-min.
25 Mar | Wed | 5+ | +$300 | Daily target hit | Daily target $300 hit cleanly. Bot shut down correctly.
26 Mar | Thu | 2 | -$186 | Session ended | Trade 1: Long at 24,287 → -$300 (50pt SL). Trade 2: Short → +$114. NQ -285pts. | Counter-trend long confirmed. Version mismatch (2 trades vs 9 on dashboard).
27 Mar | Fri | 1 | +$114 | Session ended | Short near Asian low sweep area. +$114.
28 Mar | Sat | 0 | $0 | Weekend | PDH overnight flip documented. PDH rejected 6hrs then broke above. | Reference Case 1 logged.
29 Mar | Sun | 0 | $0 | Day off | Asian low swept ~23,100. Weekly low acting as support.
30 Mar | Mon | 0 | $0 | Out of session | New week begins.
31 Mar | Tue | 2 | -$126 | NY Active | SHORT Momentum +3pts (duration). LONG Morn Star -3pts. NQ +757pts. | EMA bearish at long entry. TP at 60pts (changed). R:R 1.5:1.
1 Apr | Wed | Multiple | In progress | Active | Asian high triple rejection then flip. Full three-phase pattern observed. | Reference Cases 2 and 3 logged.
REFERENCE CASES — Evidence for v1.6 and v1.7 Build
Case | Date | Level | Pattern | What Happened | Implication | Timeframe
Case 1 | 28 Mar 2026 | PDH ~23,980 | Multi-rejection + flip overnight | PDH rejected price 6hrs. Broke above at 00:30. Level flipped to support. | Validates level flip detection for v1.6. PDH became support — longs valid on retest. | 1-min
Case 2 | 1 Apr AM | Asian High ~24,177 | Double rejection at Asian high | Touch at 07:45 (T1) and 08:00 (T2). Both rejected. 80pt drop. | Validates Asian session high as resistance for v1.7. Rejection/retest on 1-min. | 1-min
Case 3 | 1 Apr full | Asian High ~24,177 | Full three-phase — sweep + rejection + flip | Asian low swept 08:45 (long). Triple rejection at Asian high 09:30-10:30 (shorts). Flip at 10:45. Rally to 24,300+ (+367pts). | Validates all three v1.7 components in one session. Sweep long, short on retest, long on flip. | 1-min
Case 4 | 31 Mar 2026 | Prev Friday Close ~25,200 | Rejection and retest — resistance | Price from below at 10:30. First rejection + retest. Short move. Blackout 2 blocked Oracle. | Validates Prev Friday Close directional logic. Confirms Blackout 2 review (Item 8). | 5-min

## RR Analysis
ORACLE — Risk to Reward Analysis
v1.5 fixed R:R vs Three Session 2:1 vs proposed v1.6 dynamic approach
v1.5 CURRENT — Fixed TP/SL
Metric | Value | At 3 MNQ | Break-even WR | Actual WR | Assessment
Stop Loss | 30 points | $180 risk | — | — | Target setting from Week 3 onwards
Take Profit | 20 points | $120 reward | — | —
R:R Ratio | 0.67:1 | — | 60.0% | 66.9% (BT) | VIABLE — barely. Requires consistent 65%+ WR.
Week 1 R:R | 0.40:1 (TP20/SL50) | — | 71.4% | ~50% | UNFAVOURABLE — required very high WR
Week 2 R:R | 0.50:1 (TP20/SL40) | — | 66.7% | In progress | BORDERLINE
Week 3+ R:R | 0.67:1 (TP20/SL30) | — | 60.0% | TBD | TARGET — matches Run 4 backtest profile
THREE SESSION STRATEGY — 2:1 Fixed
Metric | Value | At 3 MNQ | Break-even WR | Advantage | Notes
R:R Ratio | 2:1 | Variable | 33.3% | Only need 1 in 3 trades | Mathematically superior to Oracle v1.5
SL placement | At structure | Varies | — | SL at logical level | Tighter when rejection is clean
TP calculation | 2x risk distance | Varies | — | Scales automatically | Larger wins on strong rejections
Example — Asian high | SL 30pts → TP 60pts | $180/$360 | 33.3% | $360 reward for $180 risk | 1 Apr case: ~80pt potential move
Example — Liquidity sweep | SL 35pts → TP 70pts | $210/$420 | 33.3% | $420 reward for $210 risk | 1 Apr sweep: 140pt recovery
PROPOSED v1.6 DYNAMIC R:R — Item 1a
Scenario | Rejection Candle | SL | TP (2x) | R:R | Expected Outcome
Strong pin bar at PDH | Long wick, small body | 5pts above candle high | 2x = variable | 2:1 | High conviction. Tight SL.
Engulfing at Weekly Low | Large bull body | 5pts below candle low | 2x = variable | 2:1 | Wider SL scales TP automatically.
Asian high rejection | Multiple rejections confirmed | 5pts above Asian high | 2x = variable | 2:1 | SL above level that held. TP targets prior swing.
Liquidity sweep return | Sweep wick + snap close | 5pts beyond sweep extreme | 2x = variable | 2:1 | Largest SL but largest potential TP.
Retest after flip | Level confirmed twice | 5pts beyond flipped level | 2x = variable | 2:1 | Tightest SL — level confirmed twice.